## Requirement Spec (hidden)
|  |  |  | UPDESH MANAGEMENT PLATOFRM | PLATFORM
ADMIN MENU
ZONAL KARYALAY LISTING
ZK UPDATE
UPDATE FORM
ADD KSHETRIYA KARYALAY
ACTIVE UPDASHTA LIST
ADD UPDESH :NEW /EXISTING:INDIA?
UPDESH LISTING & UPDATE
DEPENDENCY LISTING FOR DROPDOWN
ADMIN ACCESS
USER LIST
DASHBOARD
ENABLING USER ACCESS
Registration Details
|  | ACCESS REQUEST LIST | ACTION
APPROVE/REJECT REQUEST
UPDESH DASHBOARD BI Presentation
Updesh Data
Update User kkname

## TestCases (hidden)
| snapshot | functionality | url | steps | Status
TC1 |  | SIGN IN VALIDATION AS PER ADMIN ROLE | http://vyupdesh-env.eba-yziyjms4.us-east-1.elasticbeanstalk.com/ | goto url
|  |  | admin | provide userid | Done
|  |  | admin | provide pwd
Pradhan Karyalay List
TC2
PAGINATION VALIDATION
COLUMN VALIDATION AS PER DATA VALIDATION
SORTING DISABLED/ENABLED IN COL HEADER
In Progress
1.UPDATE/RESET FUNCTIONALITY BUTTON VAL
2.PAGE VALIDATION
3.DATE VALIDATION
|  |  |  | 4.COLUMN VALIDATION AS PER DATA VALIDATION | In Progress
5.SORTING DISABLED/ENABLED IN COL HEADER
TC3 |  |  |  | 6.COMMMENTS BOUNDARY VALUE ANAYSIS
TC4 |  |  |  | 1.UPDATE FUNCTIONALITY
|  |  |  | 2.PUT MANDATORY FIELDS | In Progress
3.EMAILID VALIDATION
4.OPTIONAL FIELD VALIDAQTION
TC5 |  |  |  | 1.ADD
2.PUT MANDATORY FIELDS
In Progress
3.EMAILID VALIDATION
4.OPTIONAL FIELD VALIDAQTION
TC6 |  |  | PAGINATION VALIDATION
PAGINATION VALIDATION
Count of data
T6
ACTIVE UPDESHTA LIST
TC7
RESET VALIDATION
7TC8
TC9
UPDESH LIST
List with UPD VALIDATION
TC10
[6 empty] | ADD | UPDESH
ADD UPDESH FIELD VALIDATION
TC9
TC11
LANGUAGE VALIDATION
UPDATE UPDESH

## Testing Framework Arch
Framework Setup | Activity | Technical terms | Status | Next Sprint | Resource
Selenium,Testng,Java | UI automation | TestLayer Ready | Done |  | Adarsh
Maven | To run build | pom.xml | Done |  | Adarsh
MOBILE TESTING | COMPATIBLE | Testing | Manual | Appium | Adarsh
Batch Run | Regression Suite | Retry Logic | Done |  | Adarsh
Failed Scenario | Takescreenshot | BatchRun | Done |  | Adarsh
Success Scenario | Assertion | CommonMethod | Done |  | Adarsh
API & UI URL | Config File | Connection String | In Progress |  | Adarsh
DB Services | DB Utility | DB Util | In Progress |  | Adarsh
Data Validation | Extraction data from UI and Compare with DB | E2E Testing | In Progress |  | Adarsh
Data loading | Perfomance Testing | Load Testing | Manual | Gatling/Jmeter | Adarsh | Users and Data
Wireframe
1.Common Login Page | ScanPoint/Equipment/Scanpoint |  | Click on login | Implicit /Explicit Wait
2.Go to specific pages | who can go to which pages |  | Pagination
3.Once we go to scan point | Existing data in DB |  | Search | (Get API)
4.Get call | DB Operation
5.Bulk |  |  | Bulk Upload
Note on C8: Adarsh Kumar: need from dev
Note on B10: Adarsh Kumar: Based On DB Util method

## Ques
Sr No | Question | Answer | Resolution
1 | Pagination last row where it will go?
2 | Sorting on column header | Bubble Sort
3 | Search functionality? | MultiSearch
4 | Bulk upload? | sample data template
5 | Data entry through query? | DB Services method
6 | Need sql query for data validation | Based On ER diagram Query
7 | Proper spacing between all coumns?
8 | Left Panel is not upto mark look and feel?
9 | Data loading page blick should not be there?
10 | Application level exception/error msg must be validated?
11 | Success and error msg list needed | Every page msgs put validate
12 | Wireframe is there which we can refer during validation of UI?
13 | Unstructed/Structured Data loading slowness?
14 | Data integrity :12995 +-1 12996 12994
15 | DB validation same record with oracle query
16 | One Newly data validation (Data sampling ) | data save end redirect last page
17 | Hierarchical Menu | MutiSelect or Single Select

## Major_Bugs_P1
Major Bug Num | Scenario | Impact | Resolution Time | Assigned To | Rejected | Approved | InProgress | Completed | Retesting | Done(Mark for Signoff)
1
2
3
4
5
Note on L1: Adarsh Kumar: correct Data w r to row and cell

## Medium_Minor_Bugs
Bug Num | Scenario | Impact | Resolution Time | Assigned To | Rejected | Approved | InProgress | Completed | Retesting | Demo | Done
1

## TestData
role_id | user_Roles
1 | Admin
3 | Zone
5 | Region
4 | Province
5 | HomeZone

## Sheet1
To setup the environment |  | 1 |  | 3 | To set up initial base structure of the microservice
DB extract preparation |  | 1 |  | 3 | Prepare the Db extracts needed to be migrated to Scan point DB
File processor |  | 1 |  | 3 | File to handle the reading of db extracts
Db CRUD operations | 1 | 1 |  | 4 | Business logic and CRUD operations
Listener for TL 1 message | 2 |  | 1 | 7 | Socket Listener listening for EL1 messages. Communicate with ELCOm Basic Validation of incoming message and route to Message processor
Message Processor | 4 | 1 |  | 7 | Get call to API manager . API manager queries DB and returns scan point data to message processor. Check for UDLC /E2A message and accordingly route call to message formatter
Message Formatter |  | 1 | 1 | 8 | Convert the message to surv_msg format and route to Alarm MS ( right now design is to send to kafka topic )
UI Screen Scan GET call |  | 1 |  | 3 | Query API manager and return records
UI Screen design |  | 1 |  | 3 | UI query Screen to show fields /buttons
UI Screen DB Update flow |  | 1 |  | 3 | Perform update API Post call to API manager to update db data and return result
UI Screen Dbdesign (If using same screen as above |  | 1 |  | 3 | UI screen to update db data

## Release_1.0
SNO | Positive flow | SignOff
1 |  | notok
notok
notok
notok
notok
notok
notok
notok
notok
notok
notok
notok
notok
notok
notok
notok
notok

## Major_Functionality_Not_Working (hidden)
TCNO | Snapshot | Steps To Reproduce | Expected | Actual
1 | Mandatory fields with no data validation
|  | 1.Click on add Updeshta | 1.Mandatory field Data validation | 1.No validation found
2.Fill Data as per snapshot
3.Click on add button
2 | Application Error with no proper message
|  | 1.Click on add Updeshta | 1.Proper msg should display at data column level itself or restrict user for invalid data | 1.No proper msg is found in mandatory field
2.Fill Data as per snapshot
3.Click on add button
4.Check application error
3 | Add K K application error with no proper exception message
|  | 1.Click on add KK | 1.Proper msg should display at data column level itself or restrict user for invalid data | 1.No proper msg is found in mandatory field
2.Fill Data as per below snapshot
3.Click on add button
4.Check application error
4 | Add K K data insertion
|  | 1.Click on add KK | 1.Proper msg should display at data column level itself or restrict user for invalid data | 1.No proper msg is found in mandatory field
2.Fill Data as per below snapshot
3.Click on add button
4.Check application error
5 | Add Updesh Error
|  | 1.Click on add Updesh | 1.Proper msg should display at data column level itself or restrict user for invalid data | 1.No proper msg is found in mandatory field
2.Fill Data as per below snapshot
3.Click on add button
4.Check application error
6 | Application error
7 | Add Updesh with below data
1.Click on add Updesh
2.Fill Data as per below snapshot
3.Click on add button
4.Check application error
5.Refresh page
8 | add button is not working if we will refresh page with above data | 1.Click on add Updesh | 1.Add button should work | 1.Add button is not working
2.Fill Data as per below snapshot
3.Click on add button
4.Check application error
5.Refresh page
6.Fill Data again as per snapshot
7.Click on add button